| Key Issue 1 | To ensure that the curriculum does precisely identifies what pupils need to know |
| --- | --- |
| Success criteria (targets) | Pupil’s will develop their understanding of a subject over time in a logical way Key Knowledge that the children need to learn will be identified Key knowledge will be planned in a sequential way |

| Action | Lead person | Target Dates | Performance milestones | Monitored By | Monitoring Strategy | Resources / Finance / CPD | Evaluation |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Teachers will continue to attend cluster moderation exercises | HE/LG / HG | Start September 2019 | Judgements will be consistent across the cluster | SS | Attendance at cluster events | Time | Staff are attending meetings again. Staff have visited Heath Primary to see their teaching of Little Wandle Staff need to continue to attend meetings and cluster events |
| Vocabulary will continue to be built upon across year groups and key stages through the curriculum | All staff | September 2022 | EYFS vocabulary (planned learning and child initiated will be shared each term and built up to ensure continuity | SS | Evident on planning | Time |  |
| Re – evaluate curriculum for effective vocabulary building and use of key words. Ensure vocabulary is extended and reinforced | All staff | Ongoing | Vocabulary linked to topics will be evaluated and key words used | SS | Lists made Children using words in writing | Time | Vocabulary towers seen in classrooms Vocabulary needs to be seen on short term planning and emphasised by all staff |

| Key Issue 2 | To maintain and continue to raise the improved standards in mathematics across the school by: - Quality first teaching - Maths as morning work - Number being a focus for until December across all classrooms |
| --- | --- |
| Success criteria (targets) | Mathematics standards will be at least maintained |

| Action | Lead person | Target Dates | Performance milestones | Monitored By | Monitoring strategy | Resources / Finance / CPD | Evaluation |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Teaching will be high quality | HE/ SS / LG | Start September 2021 | Teaching will be at least good in all lessons. Pace of lesson will be fast and engaging | SS | Observations / book scrutiny | N/A | One book scrutiny undertaken and changes made to expectations |
| Number will be a mathematical focus until Christmas. | LG/ HE/ SS | Start September 2021 | Consolidation of number will accelerate progress in all areas of maths | SS | observation | Teaching time | Completed |
| Mathematical displays will be seen across the school to include mathematical vocabulary | LG/ HE | Start September 2021 | Displays will be visible in all areas | SS / Link Governor | Learning walk | Time |  |
| Vocabulary will be emphasised through teaching in every lesson | LG / HE / SS | September 2021 start | Vocabulary will be used by the children. Vocabulary will be understood | SS | Observations | Time |  |
| Incorporate maths and numbers into child led activities in line with the new EYFS requirements | LG / HE | September 2021 | Children’s ideas will be accounted for in planning. Maths and numbers will be planned for alongside those ideas | SS | Evident on planning | Time |  |

| Key Issue 3 | To ensure that all children from their starting points in September make at least expected progress in Writing - Having a focus on quality - Spending more time looking at vocabulary - Using books and text as a stimulus for writing - Vocabulary and word awareness will be a feature of planning |
| --- | --- |
| Success criteria (targets) | There will be an increase in the children making good progress in writing Writing will be visible across the school |

| Action | Lead person | Target Dates | Performance milestones | Monitored By | Monitoring Strategy | Resources / Finance / CPD | Evaluation |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Teachers will continue to attend cluster moderation exercises | HE/LG / JD | Start September 2019 | Judgements will be consistent across the cluster | SS | Attendance at cluster events | Time |  |
| Writing displays will be seen across the school | LG/ JD / HE | ongoing | Displays will be seen across school | Link Governor / SS | observations | £100 |  |
| Re – evaluate curriculum for effective vocabulary building and use of key words. Ensure vocabulary is extended and reinforced | Teaching staff | Ongoing | Vocabulary linked to topics will be evaluated and key words used | SS | Lists made Children using words in writing | Time | Ongoing but started |
| Vocabulary will be extended to use anchor words, Goldilocks words and Step on words for each topic. Evidence of this will be seen in classroom displays | Teaching staff | Re-start September 2021 | Staff will become more aware of vocabulary use and increase expectations of children to use this vocabulary. | SS | Planning Lesson observations | staff meeting and planning time |  |
| Early Talk boost activities will extend vocabulary. Words will be added to the word tree and children will develop their word awareness | LG | Re-start September 2021 | Word tree will be added. Vocabulary awareness will be increased | SS | Observation Classroom display | Word tree Time |  |
| Vocabulary will be built upon across year groups and key stages | All staff | September 2021 | EYFS vocabulary (planned learning and child initiated will be shared each term and built up to ensure continuity | SS | Evident on planning | Time |  |
| Incorporate writing into child led activities in line with the new EYFS requirements | LG / HE | September 2021 | Children’s ideas will be accounted for in planning. Writing will be planned for alongside those ideas | SS | Evident on planning | Time |  |

| Key Issue 4 | To liaise with the local authority and respond to issues to develop the school further to become an all through Primary School |
| --- | --- |
| Success criteria | Consultations will be successful The local authority will work with the school to grow the school community Parents will apply for Year 3 places Year 3 children will start in September 2022 Buildings will be erected |

| Action | Lead person | Target Dates | Performance milestones | Monitored By | Monitoring strategy | Resources / Finance / CPD | Evaluation |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Liaison with Jenny Webster from local authority | SS | September 2021 | Plans will be made and permissions agreed. | Local Authority | Discussion of plans | Communication lines | Plans completed and signed off |
| Liaison with architect | Jenny Webster | Start 2021 | Designs and practicalities will be discussed | GB | Discussions at meetings | Communication minutes |  |
| Site meetings will be undertaken | Jenny Webster | 2022 | Building will start | Local Authority | Meeting discussions | Time |  |
| Appointment of KS2 staff | SS | 2021 | Staff appointed and trained. Staffing structure discussed. | GB | report back to school | Governing Body meeting |  |

| Key Issue 5 | To become an Artsmark school by; - Working with Mighty Creatives - Working with cluster schools on art project - Working with cluster schools to gain funding |
| --- | --- |
| Success criteria | School will become an Artsmark school. Children will have enhanced arts experiences and The Arts will be more visible across the school. THIS PRIORITY WILL CONTINUE DUE TO COVID RESTRICTIONS BEING IN PLACE |

| Action | Lead person | Target Dates | Performance milestones | Monitored By | Monitoring strategy | Resources / Finance / CPD | Evaluation |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Joint activities with cluster schools | SS | ONGOING | opportunities for children will be enhanced | Governors | Discussion of plans | Training and staff release time |  |
| Arts related visits and visitors will be increased to enhance understanding and provision and inspire children | SS – all staff ideas | ongoing | Children will be able to discuss | SS | Visibility across school | Financial contribution from parents for visits | Arts staff meeting held. Project with children due to start 19/01/22. Illness delayed start Artist in residence began work with the children into March 2022. |
| Dance and The arts will be explored | SS | ongoing | More opportunities will be provided for all children in regard to the arts. | Governors | Activities in school and after school clubs | Finance SSP time Teacher knowledge – coaches to train teachers and work alongside | A dance specialist will be employed for a term to work both with the children and staff to develop dance. This will begin post Easter 2022 |
| Specialist knowledge and funding will be drawn upon from a critical friend | SS | Start March 2022 | Sara has spoken to Vanessa Oxspring 07970 807063 regarding funding and further projects Vanessa to send Sara information regarding freelance dance sessions/ Arts projects that could be funded for school etc. | Governors | Practical activities offered to children in school | Potential funding Sports funding for dance specialist training |  |

| Key Issue 6 |  | - Planning across the school and into Key stage 2 as the school develops will build on prior learning and progression of vocabulary and topics |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Success criteria |  | Provision will be seamless across the school Prior learning will be built upon from week to week, term to term, year to year Prior learning will be reminded and revisited Vocabulary will be built upon |  |  |  |  |  |  |
| Action | Lead person |  | Target Dates | Performance milestones | Monitored By | Monitoring strategy | Resources / Finance / CPD | Evaluation |
| Planning to be re-evaluated across the school as children return from covid closures | SS |  | Start September 2022 | Planning to be re-looked at and changed to reflect missed learning opportunities | Governors | Discussion of plans | Training and staff release time INSET days |  |
| Planning to reflect vocabulary progression | Class teachers |  | Start September 2022 | Teachers to use rockets to display vocabulary hierarchy. | SS | Visual display | Displays |  |
| Planning to be continued across mixed age classes as the school develops into a primary school. Rolling programmes to be developed which extend learning opportunities | HG/ SS |  | Summer term 2022 | Heather will join the staff for a planning day Planning across the school will be joined up and progressive | Governors | Long term and medium term plans | INSET time Staff meeting time |  |
| Children to be regularly reminded of previous learning to ensure ‘sticky learning’ | SS |  | January 2022 | Floor books will be revisited in classrooms to remind children of what they have learnt previously Prior learning will be revisited during lessons | SS | Lesson observations | Planning |  |