5 Pits Partnership of Schools (5PPS)

Development Plan 2019-20

This Plan is a STATEMENT OF THE COLLECTIVE INTENTIONS

of the formal collaboration of Tibshelf community of schools called 5 Pits Partnership of Schools (5PPS)

The Plan is intended to give a framework for the group’s collaborative work which becomes ever more important in the current climate, which encourages a self-improving school system that has the capacity and shared ambition to drive school improvement to raise standards of teaching and learning for all pupils in all our schools aged 3 -18 through:

The aims of 5PPS are to:

- Raise aspiration of children staff and governors by offering high quality, inclusive and enriching learning experiences

- Secure strong strategic leadership

- Maintain and develop individual character, ethos and distinctiveness of each school.

- Achieve economies of scale of 5PPS to ensure cost effective services, including training and development

5PPS has the following working groups that meet regularly:

- Headteachers working group

- Chair of Governors working group

- Curriculum moderation groups

- Subject Lead/coordinator meetings

- EYFS working group

- Pastoral group

- Business managers group

- SENDco Working Group

Schools in 5PPS

| Blackwell Primary School | Newton Primary School | Tibshelf Infant and Nursery School |
| --- | --- | --- |
| Heath Primary School | Pilsley Primary School | Tibshelf Community School |
| Mickley Infant School | Shirland Primary School | Town End Junior School |
| Morton Primary School | Stonebroom Primary School | Westhouses Primary School |

| Key Priority 1 | To continue to strengthen the successful formal collaboration amongst the Tibshelf cluster of schools |  |
| --- | --- | --- |
| Success Criteria | - All stakeholders within the 5PPS are aware of the formal collaboration and understand what it is and why it has been set up. - A formal timetable of meetings and events has been created, agreed and shared amongst all stakeholders - Key skills audit of 5PPS analysed and shared amongst schools. - 5PPS Student council timetable established - Savings will be made to all school budgets as a result of sharing resources and using the group’s collective procurement powers. - Collaborative response to current national picture in education including funding |  |
| Evaluation | Evidence: Meeting minutes (DC) Audit analysis Governor’s Budget meetings minutes (all schools) 5PPS Pupil parliament Minutes | Impact: Formalised collaboration is running successfully Coordinated approach Improved budgets |

| Action | Persons/Group responsible | Monitored by | Target dates | Resources/cost/INSET | Completed/details |
| --- | --- | --- | --- | --- | --- |
| Reform Headteacher working groups/triads for school improvement | Cluster Heads | Cluster Heads | Autumn 2019 | N/A | Gp 1 – Blackwell, Westhouses, Stonebroom, Town End (vocabulary & phonics) Gp 2 – Tibshelf Infant, Newton, Mickley, Pilsley (vocabulary) Gp 3- Shirland, Heath, Morton (progress & PP) |
| Working groups/triads to meet and feed back to Cluster Heads | Triads/Quads | Cluster Heads | Summer 2020 | N/A |  |
| Share feedback from EEF & Derbyshire School Improvement Projects. | Cluster Heads | Cluster Heads | Summer 2019 | N/A | Heath – DFE workload reduction toolkit pilot. Maths Hub early years. Pilsley – GRIP format & Autism review re-Isos Stonebroom – P4C EEF Initiative- Tibshelf Town End – Maths Hub Newton – Maths Hub Westhouses – Maths Hub Morton – Reading Pals UK – EEF & Coventry University. Blackwell & TCS & Westhouses & Town End – Y5-7 Reading/vocabulary project. |
| Tibshelf to facilitate the cluster C of G meetings | Cluster Chairs | Cluster Heads | Ongoing | N/A | First meeting 9th October 2019 at 6.30pm |
| Use the 5 PPs Secure area on the internet | Pilsley | Cluster Heads | Autumn 2019 | N/A | Pilsley to train other school users. |
| Review shared memorandum of understanding | Cluster Heads & Governor | Cluster Heads | Annual review – September 2019 | N/A | Agreed October 2019 |
| To develop a plan of support for schools who potentially require improvement | Cluster Heads | Cluster Heads | Summer 2020 | N/A |  |
| To finalise planning dates of INSET DAY | Cluster Heads | Cluster Heads | Ongoing | To be organised |  |
| Update the key skills audit to include teachers, support staff & Governors & use to support SIP | Cluster Heads All cluster staff | Cluster Heads | Discuss termly | N/A |  |
| To research partnership schools joining a Teaching school alliance | Cluster Heads | Cluster Heads | Ongoing |  | Alfreton Nursery TSA- Westhouses, Morton, Pilsley, Mickley, Stonebroom, Blackwell, Heath 4Derbyshire - Newton |
| To consider how a pot of partnership funding could be negotiated and managed to provide for partnership events and training. | Cluster heads Governors | Cluster Heads | Ongoing over year | N/A | £500 per school for Artsmark schools. |
| Maintain awareness of academisation developments. | Cluster heads Governors | Cluster Heads | Ongoing | N/A | Heath became a member of the ‘’Embark Federation Trust’ on 1st January 2019. |
| Continue to raise the profile of the formal collaboration, especially through school websites. | Cluster Heads & Governors | Cluster Heads | Ongoing | N/A | On all websites & banners |
| To consider shared costs for some traded services i.e. insurance structures/services | Cluster heads Governors | Cluster Heads | Ongoing | N/A | Look at cleaning, caretaking, attendance |
| To look at budget aspects to consider long term savings through business managers meeting regularly. | Business managers/ TCS to lead | Cluster Heads | Ongoing-termly meetings | N/A | TCS to set up. |

| Key Priority 2 | Improve pupil outcomes |  |
| --- | --- | --- |
| Success Criteria | - Sharing school priorities and data - Agree on common areas to improve quality of education through teaching and learning - Develop and action a plan to improve shared area within groups across schools |  |
| Evaluation | Evidence: Cluster heads meeting minutes Data analysis Shared individual action plans | Impact: 85% Pupils in all schools, including disadvantaged achieving expected outcomes at least in-line with national expectations. |

| Action | Persons/Group responsible | Monitored by | Target dates | Resources/cost/INSET | Completed/Details |
| --- | --- | --- | --- | --- | --- |
| To share impact of pupil premium spending to ensure better outcomes for disadvantaged pupils including sharing good practice to support PP families and develop a HA PP project. Focus for working groups/triads & feedback termly to cluster meeting. | Triads | Cluster Heads | Termly (start Autumn 2019) | N/A | Working group to be set up on 24th October 2019 at Heath. |
| To audit EAL and SEND provision in the cluster and look at resources and interventions that improve progress | Cluster Heads | Cluster Heads | Autumn 2019 | N/A | Discussed at SENDco meeting November2019. |
| To audit SEN provision and have robust strategies which could be deployed across cluster to improve teaching and learning | Cluster Heads | Cluster Heads | Each Senco cluster meeting | N/A | Pilsley to investigate potential autism outreach for local schools in conjunction with DCC |
| Continue to share data from Year 6 tests to agree a common assessment foci | Cluster Heads | Cluster Heads | Annual – Autumn Term | N/A | Carried out in Triads |
| To share good practice to support PP families through enhancing the skills of learning mentor/play leaders | Learning mentors/play leader meetings | Cluster Heads | Ongoing | N/A | Learning mentors to continue to meet. |
| Primary schools work with TCS to share data and progress reports (including vulnerable groups.) | TCS | Cluster Heads | When suitable | N/A | Pilsley to invite TCS to see Y6 groups. |

| Key Priority 3 | Promote staff professional development and wellbeing |  |
| --- | --- | --- |
| Success Criteria | - Teacher’s judgements will be validated ensuring confidence in accurately assessing children’s work. - Improving staff understanding of the importance of effective cross-phase transition - Development of middle leadership in key areas - Sharing school priorities and identifying common areas for improvement of staff professional development - School staff will be empowered and valued through working collaboratively with colleagues in other schools |  |
| Evaluation | Evidence: Moderation feedback Transition questionnaires Pupil interviews Curriculum group meeting minutes Staff questionnaires | Impact: CPD enhanced through collaborative working Middle leaders feel empowered Staff voice valued in decisions Improved pupil outcomes Staff survey shows they feel valued and have a positive work/life balance |

| Action | Persons/Group responsible | Monitored by | Target dates | Resources/cost/INSET | Completed/Details |
| --- | --- | --- | --- | --- | --- |
| To decide a yearly overview plan for moderation meetings | Cluster Heads | Cluster Heads | Timetable made during Autumn Term 2019 |  |  |
| HPS to take part in the DFE workload reduction toolkit pilot | Heath PS | Cluster | 2019-20 |  | Heath to feedback and share the process |
| Investigate the need to provide for NQT support and guidance | Cluster Heads | Cluster Heads | Discuss at each meeting | NQT time | Tibshelf Infant to lead |
| To set up termly SEND cluster meetings | Cluster Heads | Cluster Heads | Set dates Autumn 2019 | N/A | Autumn meeting – 20th November 2019 |
| To widen staff opportunities to work and have experience at other schools – link to skills audit | Cluster Heads | Cluster Heads | Spring 2020 | Post skills audit | Pilsley staff to visit other schools in March 2020 TCS to be invited to visit English & Maths. Schools invited to join the Y5-7 reading/vocabulary project |
| To support partnership schools with recruitment and interviewing | Cluster Heads & Governors | Cluster Heads | Ongoing | N/A |  |
| To develop and enhance knowledge, skills of TA staff – i.e. send staff to other schools, TA learning walk | Cluster Heads | Cluster Heads | Spring 2020 | Time allocated to release TA |  |
| To share good practice from staff who have undertaken professional qualifications. | Cluster Heads | Cluster Heads | Spring 2020 | N/A |  |

| Key Priority 4 | Raise aspirations through enriching pupils’ wider learning opportunities |  |
| --- | --- | --- |
| Success Criteria | - Programme of shared 5PPS, community of schools, events - Children will be given a greater voice in decision making and their learning through the 5PPS student’s council. - Enhanced transition, curriculum and community activities - Develop learning for life skills whilst enhancing cultural capital opportunities. |  |
| Evaluation | Evidence: Timetable shared activities 5PPS student council feedback on websites School display board | Impact: - Improved health, wellbeing and enjoyment of learning through the commitment to curriculum and wider community activities. - Higher aspirations for all pupils. |

| Action | Person/Group responsible | Monitored by | Target dates | Resources/cost/INSET | Completed/details |
| --- | --- | --- | --- | --- | --- |
| To further develop Forest Schools curriculum and resources | Forest School Leaders | Cluster Heads | Termly | Time |  |
| Maintain a 5PPS student council | School Council Leaders from each school | Cluster Heads | Autumn term 2019 |  | Dates set: Heath – November 14th 2019 Blackwell – 27th Feb 2020 Westhouses – 18th June 2020 |
| Set up Artsmark meetings for leads. | Westhouses & Town End to lead | Cluster Heads | All year | £500 per school for Arts Mark | Arts leads to carry out pupil questionnaires, subject leadership time, develop skills ladders. Agree bursary spending. |
| Discuss how schools look after the well-being of staff | All Heads | Cluster Heads | Autumn 2019 | Time | To be discussed at staff meeting. |